## Sheet1
Weekly Log
Project Title: El. Mars
Team Members: | Nirjal Bhurtel (12)
Dipen Khatri (23)
Roshan Sahani (41)
Asim Shrestha (48)
Supervisor: | Manish Joshi
Week No. | Tasks Targeted | Task Accomplished | Problem Encountered | Team Members
|  |  |  | Nirjal Bhurtel | Dipen Khatri | Asim Shrestha
Pre Preparation | Collect Nasa Resources, and some open-source elements and blender files. | Collected Resourses and 3d Models which was static | All the models were static so had to do texture and animations
Week 1 (Feb. 10) | Terrain dtm with the confined territory, good texture and rendering quality. Import the terrain on unreal engine and adjusted its scale. | Imported dtm gale crater 3d terrain in blender. This was then imported in unrealengine in .fbx format. | Dtm gale crater terrain was of good rendering quality but importing in UE was of very small in size and, texture had to be managed
Week 2 (Feb. 17) | Import Curiosity's 1.8-Billion-Pixel Panorama and convert it in hdr image. Import this pano in unreal using hdr plugin | Imported real panorama by curiosity in unreal thorugh hdr plugin. | Quality of the terrian was not good as it scales up because it was image over a default plane.
Week 3 (Feb. 24) | To manage the quality of terrian in confined territory and also bring the model of Perseverence in blender with animations. | Quality of terrian was clear in just 10 by 10 scale. Perseverence was brought in blender with animations. | Panorama Terrian was not of good quality as expected. Brought dtm gale crater with good quality and texture but it had problem with plane.
Week 4 (Mar. 3) | Bring vechile in plane and move it with standard controls using c++ code. Make an astronaut in blender with animations and movement | Car was made to move in simple plane with landscapes and highmaps with texture of mars but, not in real terrian. 3d model of an astronaut was imported with blender. | Movement of Perseverence and astronaut in plane of terrian. Animations of astronaut.
Week 4 (Mar. 10) | Make the astronaut animations and rig the vechile animations | Animations for the characters were done using Adobe mixamo. | Riging the vechile animation
Week 5(Mars. 17) | Add the landmark in terrains and build lighting and particle systems | Astronaut with all the animations in the real mars terrain were imported and all the input processing was done accordingly | Animations were not that good enough to be realistic but is good enough for prototying. For adding the mars space vechile riging it was a problem
Week 6 (Mars. 24)